## Sheet1
Sprint Sheet - Sprint 1
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day-14
Architecture Diagram | Deciding on the workflow | Ishan | 14 | 2021-10-16: 2; 2021-10-18: 1; 2021-10-19: 3; 2021-10-20: 2; 2021-10-24: 3; 2021-10-25: 2; 2021-10-26: 1
UI Wireframes | Working on mock UI screens | Shaunak | 14 | 2021-10-14: 2; 2021-10-15: 2; 2021-10-18: 2; 2021-10-21: 2; 2021-10-22: 3; 2021-10-24: 1; 2021-10-26: 2
Front End Technology Search | Deciding on front end technology | Tejas | 14 | 2021-10-14: 3; 2021-10-15: 1; 2021-10-16: 2; 2021-10-17: 1; 2021-10-19: 4; 2021-10-22: 2; 2021-10-24: 1
AWS Search | Exploring aws deployment options | Jash | 14 | 2021-10-19: 4; 2021-10-20: 3; 2021-10-22: 2; 2021-10-23: 1; 2021-10-25: 1; 2021-10-26: 2; 2021-10-27: 1
Remaining Effort |  |  | 56 | 51 | 48 | 44 | 43 | 40 | 29 | 24 | 22 | 15 | 14 | 9 | 6 | 1 | 0
Ideal Trend |  |  | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Sprint Sheet - Sprint 2
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day-14
Backend - API for creating a new booking | Admin should be able to add a new flight | Ishan | 14 | 2021-10-28: 3; 2021-10-29: 2; 2021-10-31: 4; 2021-11-02: 3; 2021-11-03: 2
Admin UI Screen | Edit flight information - Admin | Shaunak | 10 | 2021-10-28: 4; 2021-10-29: 3; 2021-11-01: 1; 2021-11-02: 2
Customer Landing Page | Customer Screen landing page / Customer Dashboard | Tejas | 14 | 2021-10-28: 4; 2021-10-30: 3; 2021-10-31: 2; 2021-11-01: 2; 2021-11-03: 3
Customer registration and Login | Backend Implementation | Tejas | 14 | 2021-10-28: 3; 2021-10-29: 1; 2021-10-30: 3; 2021-11-01: 3; 2021-11-02: 2; 2021-11-03: 2
Dashboard - Admin | Dashboard UI component - Admin | Jash | 4 | 2021-10-28: 2; 2021-10-30: 2
Remaining Effort |  |  | 56 | 40 | 34 | 26 | 20 | 14 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Trend |  |  | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Sprint Sheet - Sprint 3
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day-14
Update Mileage Points - Backend | Backend API for Updating the user booking | Ishan | 14 | 2021-11-14: 2; 2021-11-16: 1; 2021-11-18: 3; 2021-11-19: 1; 2021-11-21: 2; 2021-11-23: 2; 2021-11-24: 3
Cancel a booking - Admin | Changing the price UI component - Admin | Jash | 9 | 2021-11-16: 2; 2021-11-18: 3; 2021-11-20: 1; 2021-11-23: 2; 2021-11-24: 1
UI for admin dashboard | UI screen for checkout | Jash | 14 | 2021-11-15: 2; 2021-11-16: 3; 2021-11-17: 2; 2021-11-18: 2; 2021-11-21: 2; 2021-11-22: 1
Login functionality | Integration of Backend with frontend for login screen | Tejas | 14 | 2021-11-14: 1; 2021-11-15: 1; 2021-11-19: 3; 2021-11-21: 5; 2021-11-23: 1; 2021-11-24: 3
Checkout - Backend | Add new Flight UI component - Admin | Shaunak | 5 | 2021-11-17: 1; 2021-11-19: 2; 2021-11-24: 2
Remaining Effort |  |  | 56 | 56 | 56 | 56 | 53 | 50 | 44 | 41 | 33 | 27 | 26 | 17 | 16 | 11 | 2
Ideal Trend |  |  | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Sprint sheet -Sprint 4 | bar: 2021-11-11 to 2021-11-18
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02
|  |  | Day 0 | Day 1 | Day 2 | Day 1 | Day 2 | Day 1 | Day 2 | Day 1 | Day 2
Cloud - AWS EC2 cluster deployment | Deployment on AWS EC2 cluster | Jash | 4 | 2021-11-29: 2; 2021-12-02: 2
Customer UI Integration and Admin UI Integration | Backend API integration with front end | Tejas | 7 |  | 1 |  | 3 | 1 | 2 | 2 | 1
Customer UI Integration and Admin UI Integration | Backend API integration with front end | Ishan | 7 | 2021-11-27: 2; 2021-11-29: 2; 2021-12-01: 2; 2021-12-02: 1
Customer UI Integration and Admin UI Integration | Backend API integration with front end | Shaunak | 7 |  |  | 1 | 2 | 1 | 3 | 3 | 1
Remaining Effort |  |  | 32 | 32 | 31 | 28 | 23 | 17 | 12 | 5 | 0
Ideal Trend |  |  | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0